| Action Team/Item | Lead(s) | Status | Next Steps/Expected Significant Results by 9/30/05 | Recommendations supported by PM & C |
| --- | --- | --- | --- | --- |
| Communicating the Message |  |  |  |  |
| Business Case | D. DiSera D. Nebert | Revised Action Plan 6/05 | - Write and publish business case(s) by Aug 05 - Develop ROI workbook and Template by Sept 05 - FGDC funding needed for next phase of development | Partner with GITA to develop companion document – ROI workbook, methodology & templates to determine the business value of collaborative approach |
| Communications | L. Wollack | Report completed Accepted by CG 1-05 Original plan needs to be reviewed & updated | - Continue to work collaboratively with NGPO - Update original plan - Set up FGDC Communications Team | Establish Interagency Outreach & Communications Standing Committee or Working Group for FY 06 |
| Training & Ed | S. Shin | Metadata curriculum on line | - Expanding curriculum to include framework & GOS Portal - Clearinghouse available online 9/05 | # Solicit participation of CG in feedback and training materials inventory |
| Making Framework Real |  |  |  |  |
| Framework | J. Binder-Maitra | Work completed – sending all documents and logs to editing team in Rolla | - Once editing is complete, all parts of Framework Data Standard submitted to INCITS L1 for review | Debrief process – best practices & lessons learned |
| Next Generation of Standards | J. Binder-Maitra | Standards in development: - Shoreline Data Content - Address Data | - Proposals for standards expected to be approved by INCITS L1 by CY05 – hydrologic unit codes and geographic names - Draft of address data standard - Public review of shoreline data content standard to begin | Hold initial discussions regarding a strategy to accelerate the standards process |
| Metadata compliance | L. Wayne | Survey conducted with 70% return rate Compiling results and summary report | - Agency Metadata Profile Summary Report and Results by Sept 30 - Identify needed metadata assistance resources | Extend survey to partners in FY 06 Increase outreach to agencies and partners in FY06 |
| Consensus-based standards & Web protocols | J. Evans D. Nebert |  | - Commitment & process for adopting external standards |  |
| 133 Urban Areas | K. Covert T. McDermott | Workshop held to frame content & process 5/05 | - Metropolitan Regions Spatial Information Guidebook due 12/05 |  |
| Partnerships with Purpose |  |  |  |  |
| Governance | D. Goreham A. Voss | Report completed Recommendations 1 & 3 accepted by SC Identifying next steps for governance model Secretariat staff leading implementation of FGDC improvements | - Complete appendix & documentation of efforts by 8/05; notify & post - Complete and accept charters and workplans for FY06 - Act on recommendations #1 & #3 - Identify strategy to solicit guidance from SC members | Solicit feedback & guidance on proposed governance model & concept |
| Tribal Engagement | B. Gallahan | Outreach efforts to tribes primarily through collaborative training opportunities Forty-one (41) Tribes and more than 140 participants to date | - Three additional courses to be delivered with FWS & DHS/FEMA by Sept 30 - Continue discussions with FS for NSDI/Metadata Awareness course at FS Training Center in Feb 06 | Identify agencies/partners wishing to establish training courses at training centers or conferences in FY06 (Contact B. Gallahan) |
| State Councils | B. Burgess | Report completed; accepted by NSGIC; supported in concept by SC; USGS committed partial financial support for 06 | - Roundtable discussion at NSGIC Conference 9/05 - Develop financial & other support for the initiative | Seek final approval from SC at Fall meeting |
| Non-geospatial organizations | J. Clark L. Wollack | Report accepted by CG 5-05; Team members interested in approved FGDC post-action activities | Need implementation team to - Target participation in select number of conferences/events - Fund & implement proposed Regional Geospatial Training Pilot | Establish Interagency Outreach & Communications Standing Committee or Working Group for FY 06 Adopt & implement outreach model |
| Agreements to facilitate involvement by private sector & utilities | Ivan DeLoatch Alison Dishman FGDC Secretariat | Agreements with GITA, URISA in place FY 05 AAG requested partner status | - Identifying other Stakeholder groups for formal partnership with FGDC | Seek recommendations and assistance from Federal partners |