National Geospatial Advisory Committee

DRAFT Implementation Schedule

2-6-07

| Date | Action | Status |
| --- | --- | --- |
| 10-23-06 | FGDC Steering Committee: Advisory vote on creating FACA Committee | Complete |
| 11-06 | FGDC Coordination Group: Discussion of FACA Committee/next steps | Complete |
| 12-5-06 | FGDC Coordination Group: Discussion of FACA Committee. - Distribution of draft Committee charter for review/comment | Complete |
| 1-12-07 | Comments due on draft committee charter | Complete |
| 1-16-06 | FGDC Coordination Group: Review of comments on draft charter, discussion of revised draft charter | Complete |
| 2-6-07 | FGDC Coordination Group: Overview of FACA presentation for 2-15-07 Steering Committee meeting, review of revised final FACA documents (charter, call for nominations, schedule, etc.) | Pending |
| 2-15-07 | FGDC Steering Committee: Presentation on FACA charter/Call for Nominations/next steps | Pending |
| 2-07 | FGDC Chair issues Call for Nominations (45 day response period) | Pending |
| 4-07 | Review Team analyzes nominations, makes recommendations to DOI Office of the Secretary | Pending |
| 5-07 | DOI Office of Secretary reviews recommendations, makes membership selections | Pending |
| 5/07 | Committee approval package (final charter, appointment letters, etc) reviewed/approved by Office of Secretary | Pending |
| 6/07 | Final committee charter is filed with GSA Office of Committee Management | Pending |
| 6/07 | Notice of Committee establishment is posted in Federal Register for 15 days. | Pending |
|  | Following 15-day FR notice period, committee meetings may be held. | Pending |