## Slide 1: NSDI Strategic Plan Update
January 14, 2014

## Slide 2: NSDI Strategic Plan High-level Timeline
Timeframe | Activity
Dec - Feb | Project Start-up – COMPLETED
Feb - Sept * | Outreach to external partners, key individuals, professional meetings, social media, etc. – COMPLETED
March 5 * | Strategic Visioning Workshop – COMPLETED
March 7 * | NSDI Leaders Forum – COMPLETED
Feb - March | Develop expanded outline of Strategic Plan – COMPLETED
March 19 * | FGDC Steering Committee Meeting – COMPLETED
April 3 * | NGAC Webinar Meeting – COMPLETED
April - May | NGAC Subcommittee input – COMPLETED
April - May | Develop initial draft Strategic Plan (v1) – COMPLETED
June 11 - 12 * | NGAC Meeting – COMPLETED
June 13 * | FGDC Steering Committee Meeting – COMPLETED
June 19 * | NSDI Leaders Forum II – COMPLETED
June - July | Develop revised draft Strategic Plan (v2) – COMPLETED
July - Aug * | Public Comment Period – COMPLETED
Aug 26 * | NSDI Leaders Forum III – COMPLETED
Sept 4 - 5 * | NGAC Meeting – COMPLETED
Sept 12 * | FGDC Steering Committee Meeting – COMPLETED
Oct - Nov | Develop Final Draft Strategic Plan (v3) – COMPLETED
Dec 11, 2013 | NGAC Endorsement of Strategic Plan – COMPLETED
Dec 13, 2013 | FGDC Approval of Strategic Plan – COMPLETED
*Opportunities for public/partner input
December 2013

## Slide 3: NSDI Plan – Final Draft Version (v3)
Final Draft Plan addressed comments received through Public Comment Period & recent meetings with Steering Committee, NGAC, and Leaders Forum group:
  Changed order of document (moved goals to front)
  Added new Actions on Geolocation Privacy and International Programs
  Added language on Strategic Plan drivers (e.g., A-16 & GAO report)
  Added detail on implementation process
  Consolidated sections on Vision/Guiding Principles
  Added detail on coordination with non-Federal partners and roles and responsibilities of the NGAC
  Added references to alignment with Open Data Policy
  Clarified language on alignment between geospatial and IT programs
  Added glossary of abbreviations & terms
  Editorial changes for clarity and consistency

## Slide 4: NSDI Strategic Plan – Final Version
FGDC Steering Committee
Final Draft distributed to Steering Committee on December 5 for electronic vote.
Approved by Steering Committee – December 13, 2013
National Geospatial Advisory Committee
Final Draft reviewed and considered at December 11 NGAC public meeting
Endorsed by NGAC – December 11, 2013

## Slide 5: A Shared Vision for the NSDI
The FGDC has worked with partners and stakeholders, including the members and organizations represented on the National Geospatial Advisory Committee, to collaboratively define a shared national vision that describes the value that the NSDI will bring to its stakeholders and partners.
NSDI Vision Statement
The NSDI leverages investments in people, technology, data, and procedures to create and provide the geospatial knowledge required to understand, protect, and promote our national and global interests.

## Slide 7
STRATEGIC GOAL 1:
Develop Capabilities for National
Shared Services
Objective 1.1. Develop geospatial interoperability reference architecture
Objective 1.2. Establish the Geospatial Platform as the Federal geospatial
data, services, and applications Web-based service environment
Objective 1.3. Expand the use of cloud computing
Objective 1.4. Promote the use of geospatial multiagency acquisition
vehicles for interagency and intergovernmental purchases

## Slide 8
STRATEGIC GOAL 2:
Ensure Accountability and Effective
Development and Management of
Federal Geospatial Resources
Objective 2.1. Advance the portfolio management process for
National Geospatial Data Assets (NGDA)
Objective 2.2. Identify potentially duplicative investments and
opportunities for collaborative investments

## Slide 9
STRATEGIC GOAL 3:
Convene Leadership of the
National Geospatial Community
Objective 3.1. Lead and participate in the development and coordination of
national and international standards applicable to the geospatial community
Objective 3.2. Convene the leadership of the geospatial and nongeospatial
communities to develop public/private partnerships and shared approaches
for addressing critical national issues
Objective 3.3. Raise awareness of the NSDI and its impact on critical
national and international issues

## Slide 10: NSDI Plan – Implementation
  FGDC Executive Committee will have the lead responsibility for overseeing and monitoring implementation of the plan.
  NSDI Core Team developing draft implementation framework.
A designated Federal official will serve as the champion for each strategic goal. Champions will report to the FGDC ExCom and Steering Committee.
Champions will be responsible for overseeing team leaders and action teams addressing each objective and its supporting actions.
Action team leaders will develop project plans outlining how the goals and objectives will be achieved. Project plans will include:
  Detailed tasks and milestones
  Timelines
  Responsible parties
  Performance indicators/measures
  Identification of resources available to achieve the objectives
The FGDC will work with the NGAC and other partner organizations to collaboratively implement the Strategic Plan.

## Slide 11
www.fgdc.gov/nsdi-plan