Objectives:

- Review FGDC standards endorsed 5 years or more, according to FGDC standards directive #9.

- Review standards in development and decide to advance development in 2006 or discontinue

Action needed:

- Review 17 current FGDC endorsed standards to determine 4 options:

  - Reissue the current standard (reconfirm with no changes)

  - Revise the current standard (recommend minor editorial and general changes)

  - Change the current standard (recommend major or technical changes)

  - Withdraw the current standard (justification: lack of need, superceded, replaced, outdated, etc)

- Review standards in development to

  - decide to advance development in 2006

  - discontinue

Overall Approach:  Use a phased approach. Focus on the oldest endorsed standards (13 established before 2000) first.

2nd Quarter – 1 standard endorsed by FGDC 1996 (pilot the process & guidance review)

3rd Quarter – 2 standards endorsed by FGDC 1997 (pilot the process & guidance review)

3rd Quarter – 7 standards endorsed by FGDC 1998 – 1999

4th Quarter – 7 standards endorsed by FGDC 2000 – 2001

Stage 1:  Planning and Preparation

- Outline process and determine schedule

- Brief and discuss with Standards Working Group (SWG)

- Draft first level of Review Guidance

- Open for comment and revisions with SWG

- Inform FGDC staff, Coordination Group, Sub-Committee and Working Group chairs

Stage 2:  Mobilization and Implementation

- Focus on the oldest endorsed standards first – start with a manageable number in each quarter

- 17 standards need review this year; 4 are current

- Contact Sub-Committee and Working Group chairs – notifying them of schedule, suggested timeframe for review

- Conduct interviews and assist in setting timeframe for review and recommendations

- Check status of proposals and drafts of other standards not yet endorsed.

Stage 3:  Act on recommendations

Project Outline

| Actions | Procedures | Responsibility | Timeframe |
| --- | --- | --- | --- |
| Outline process and frame schedule | Target by quarter Focus on oldest standards | J. Maitra with T. Gibbons | 1/30/06 |
| Brief SWG | Discuss & comment | J. Maitra with T. Gibbons | 2/8/06 SWG meeting |
| Develop guidance for review draft | Post questions in FGDC forum Compile and draft guidance Distribute for SWG review | ALL SWG JM & TG | By 2/17/06 By 2/24/06 By 3/2/06 |
| Inform FGDC staff, Coordination Group, sub-Committees and Working Groups | Brief FGDC staff for comment Brief FGDC CG Send memo to all Sub-Committee & Working Group leads | J. Maitra | 3/7/06 CG meeting |
| PILOT with 3 SC/WGs Contact leads of first set of standards (See chart below) | Send email / Contact by phone Set up phone interview Distribute guidance ahead of time Conduct interview Set timeframe for review & recommendations | J. Maitra | Mar 06 April 06 |
| Review standards – group 1 (See chart below) | Add to work plan Incorporate into semi-annual reports Led by identified sponsor | Identified sponsor | March – May 06 |
| Check progress of reviews | By phone or email | J. Maitra | On-going |
| Contact leads of next group of standards (See chart below) | Send email / Contact by phone Set up phone interview Distribute guidance ahead of time Conduct interview Set timeframe for review & recommendations | J. Maitra | May 06 |
| Review standards – group 2 | Add to work plan Incorporate into semi-annual reports Led by identified sponsor | Identified sponsor | June – Aug 06 |
| Contact leads from next group | Send email / Contact by phone Set up phone interview Distribute guidance ahead of time Conduct interview Set timeframe for review & recommendations | J. Maitra | July 06 |
| Review standards – group 3 | Add to work plan Incorporate into semi-annual reports Led by identified sponsor | Identified sponsor | Aug – Sept 06 |
| Briefing to FGDC CG | Progress reports | J. Maitra | June 06 September 06 |

Schedule:

| Quarter | Standard | Status | Date | Sponsor | Document Number | Maintenance Authority |
| --- | --- | --- | --- | --- | --- | --- |
| 2 | Classification of Wetlands and Deepwater Habitats in the United States (pilot) | FGDC-endorsed standard | 1996 | Wetlands Subcommittee | FGDC-STD-004 | Fish and Wildlife Service |
| 3 | Soil Geographic Data Standard (pilot) | FGDC-endorsed standard | 1997 | Soils Subcommittee | FGDC-STD-006 | Natural Resources Conservation Service |
| 3 | National Vegetation Classification Standard (pilot) | FGDC-endorsed standard | 1997 | Vegetation Subcommittee | FGDC-STD-005 | Forest Service |
| 3 | SDTS Part 6: Point Profile | FGDC-endorsed standard | 1998 | Federal Geodetic Control Subcommittee | FGDC-STD-002.6 | National Geodetic Survey |
| 3 | Geospatial Positioning Accuracy Standards, Part 3: National Standard for Spatial Data Accuracy | FGDC-endorsed standard | 1998 | Subcommittee for Base Cartographic Data (retired) | FGDC-STD-007.3-1998 | USGS |
| 3 | Content Standard for Digital Geospatial Metadata (version 2.0) | FGDC-endorsed standard | 1998 | FGDC | FGDC-STD-001-1998 | FGDC |
| 3 | Spatial Data Transfer Standard (SDTS), Parts 1-4 | FGDC-endorsed standard | 1998 | Standards Working Group | FGDC-STD-002 | USGS |
| 3 | SDTS Part 5: Raster Profile with Basic Image Interchange Format (BIIF) Extension | FGDC-endorsed standard | 1998 | Subcommittee for Base Cartographic Data (retired) | FGDC-STD-002.5 | USGS |
| 3 | Geospatial Positioning Accuracy Standards, Part 1: Reporting Methodology | FGDC-endorsed standard | 1998 | Federal Geodetic Control Subcommittee | FGDC-STD-007.1-1998 | National Geodetic Survey |
| 3 | Geospatial Positioning Accuracy Standards, Part 2: Standards for Geodetic Networks | FGDC-endorsed standard | 1998 | Federal Geodetic Control Subcommittee | FGDC-STD-007.2-1998 | National Geodetic Survey |
| 4 | Content Standard for Digital Geospatial Metadata: Part 1, Biological Data Profile | FGDC-endorsed standard | 1999 | Biological Data WG | FGDC-STD-001.1-1999 | USGS Center for Biological Informatics |
| 4 | Content Standard for Digital Orthoimagery | FGDC-endorsed standard | 1999 | Subcommittee for Base Cartographic Data (retired) | FGDC-STD-008-1999 | USGS |
| 4 | Content Standard for Remote Sensing Swath Data | FGDC-endorsed standard | 1999 | Standards Working Group | FGDC-STD-009-1999 | NASA |
| 4 | SDTS Part 7: Computer-Aided Design and Drafting (CADD) Profile | FGDC-endorsed standard | 2000 | Facilities Working Group | FGDC-STD-002.7 | U.S. Army Corps of Engineers |
| 4 | Utilities Data Content Standard | FGDC-endorsed standard | 2000 | Facilities Working Group | FGDC-STD-010-2000 | U.S. Army Corps of Engineers |
| 4 | Content Standard for Digital Geosptial Metadata: Part 2, Metadata Profile for Shoreline Data | FGDC-endorsed standard | 2001 | Marine and Coastal Spatial Data SC | FGDC-STD-001.2-2001 | NOAA Coastal Services Center |
| 4 | Standard for a U.S. National Grid | FGDC-endorsed standard | 2001 | Standards Working Group | FGDC-STD-011-2001 | Public XY Project |

The following standards are current and are not in need of review in FY 06.

| Quarter | Standard | Status | Date | Sponsor | Document Number | Maintenance Authority |
| --- | --- | --- | --- | --- | --- | --- |
| FY 07 | Geospatial Positioning Accuracy Standards, Part 4: Architecture, Engineering, Construction, and Facilities Management | FGDC-endorsed standard | 2002 | Facilities Working Group | FGDC-STD-007.4-2002 | U.S. Army Corps of Engineers |
| FY 07 | Content Standard for Digital Geospatial Metadata: Extensions for Remote Sensing Metadata | FGDC-endorsed standard | 2002 | Standards Working Group | FGDC-STD-012-2002 | NASA |
| FY 08 | Cadastral Data Content Standard | FGDC-endorsed standard | 2003 | Cadastral Data Subcommittee | FGDC-STD-003 | Bureau of Land Management |
| FY 10 | Geospatial Positioning Accuracy Standards, Part 5: Standards for Nautical Charting Hydrographic Surveys | FGDC-endorsed standard | 2005 | Marine and Coastal Spatial Data SC | FGDC-STD-007.5-2005 | Office of Coast Survey |

# Comments

Bill Wilen

Jim Fortner

Ralph Crawford; no work plan posted

The National Map; NDOP, NDEP

NDOP